## PURPOSE and SCOPE OF WORK

The Bureau of Land and Waste Management Underground Storage Tank (UST) Program of the South Carolina Department of Health and Environmental Control (DHEC) is seeking services to perform active corrective action of a petroleum release from a regulated underground storage tank site in accordance with defined remediation goals. The objective is to remove free product AND/OR reduce the levels of chemicals of concern (CoC) in the ground water to or below defined site-specific target levels (SSTLs).  All offerors must be South Carolina Certified Class I Site Rehabilitation Contractors.  The scope of work defined in this solicitation is to be implemented at __________ (UST Permit # ______), _________________ _____, __________, South Carolina for the release reported on ____________.

SPECIAL CONDITIONS

- CONTRACT PERIOD: The contract will be effective from date of award until the corrective action is complete as described in this contract.

- This contract is for active corrective action in addition to natural attenuation at only one (1) site in South Carolina. Compensation from the SUPERB Account is not considered a state contract for purposes of procurement or subject to state bid requirements in accordance with Section 44-2-130(D) of the SUPERB Act.

- AWARD:  Award will be made to a South Carolina Certified UST Site Rehabilitation Contractor based on the total cost, method(s), and estimated time for active corrective action to SSTLs and removal or abandonment of assessment and rehabilitation items, provided the proposed implementation schedule to achieve the remediation goals, the removal of all equipment and abandonment of wells, (including pre-existing wells), trenches, etc. installed by the contractor, and the proposed remediation technology(ies) or method(s) are protective of  public health and the environment and are eligible for permitting by DHEC.  The total cost, methods, and estimated time to complete the contract must be advantageous to the State of South Carolina.

- REASONABLE COST: DHEC reserves the right to reject any and all bids that appear to be above the customary and reasonable cost for the same scope of work in a similar geologic setting, that propose a technology that cannot be permitted in the State of South Carolina, or that propose an estimated time frame for cleanup that is not protective of human health or the environment.

- Contractor must agree to make positive efforts to use women- and minority-owned businesses.

- AMENDMENTS:  All amendments to this solicitation will be in writing from the DHEC Procurement Officer indicated on page one of this solicitation.  DHEC will not be legally bound by any amendment or interpretation that is not in writing.

- QUESTIONS:  Questions or requests for information must be submitted in writing and received by 5:00 P.M.,                                   .  After this date, no further questions will be addressed.  A written response will be mailed to all requestors of the solicitation.  The questions may be faxed to Henry Wigfall, fax number (803) 898-3505.

- NOTE . . . THE ONLY OFFICIAL CONTACT PERSON AT DHEC DURING THE SOLICITATION AND AWARDING PROCESS IS THE PROCUREMENT OFFICER INDICATED ON PAGE ONE OF THIS SOLICITATION.  OFFERORS ARE NOT TO CONTACT DHEC PERSONNEL LOCATED OUTSIDE THE BUREAU OF BUSINESS MANAGEMENT.

- The contractor will be required to treat the area where the dissolved petroleum chemicals of concern are above site-specific target levels (see figure #2).  Verification that interim corrective action goals have been met will be based upon ground-water quality samples collected from monitoring wells MW-_, MW-_, MW-__, MW-__, and MW-__.  Verification that final corrective goals have been met will be based upon ground-water quality samples collected from all existing monitoring wells, and additional verification wells to be installed at locations designated by SCDHEC (see specification #10 for more detail).

- REPORTS:  Deliver the reports to: SCDHEC, Bureau of Land and Waste Management, UST Program, ATTN: PM, 2600 Bull Street, Columbia, SC 29201.  A minimum of two (2) copies of each plan and two (2) copies of each report must be delivered to the above address.  Based on permitting and other requirements, an engineering report, UIC permits, air modeling forms or NPDES Permits may be required.  Please contact the Department for the exact number of copies of each document to be submitted.

- INVOICING:  Invoices will be submitted to: SCDHEC, Bureau of Land and Waste Management, UST Program, ATTN: Financial Section, 2600 Bull Street, Columbia, SC 29201, using the Department’s Corrective Action (CA) Invoice form. The initial invoice must be received at the above address within four months of CAP approval or funds will be uncommitted as required by the Section 44-2-40(B) of the SUPERB Act. If funds are uncommitted the submitted invoice will be held until funding is available. Payment will only be made for achieving the corrective action goals as specified in this contract. No interim or partial payments will be made once corrective action is initiated, except as outlined in Specification #2. Payment to the contractor will be a pay for performance system as follows:

A.	Payment of forty percent (40%) of the total corrective action price will be made within 90 days of operation of the remediation system or implementation of corrective action as described in the approved corrective action plan (CAP), subject to the limitations of Section 44-2-40 of the SUPERB Act.  The implementation should be documented in the first corrective action monitoring report.

- Payment of thirty-five percent (35%) of the total corrective action price will be made based on removal of free product to .01 foot as verified in monitoring wells COPY 9 and achieving interim CoC mass reduction goals at the site as verified in monitoring wells COPY 9.  Payment will be made for interim goals of 25, 50, and 75 percent reduction of total CoC mass by the implementation of corrective action.  The CoC mass requiring reduction is as follows:

CoC mass in parts per billion (g/l) based on ____________ sampling: (CoC may increase or decrease in the future)

| Well | Benzene | Toluene | Ethylbenzene | Xylenes | MTBE | Naphthalene | Total Mass |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |  |
| Initial Mass* |  |  |  |  |  |  |  |
| SSTL Mass |  |  |  |  |  |  |  |
| Initial Mass above SSTL |  |  |  |  |  |  |  |

* CoC mass may change due to seasonal fluctuations in the groundwater.

- 25 percent total mass reduction will be achieved when free product has been removed to .01 foot from COPY 9 and one-quarter of the initial BTEX, MTBE, and Naphthalene mass from monitoring wells COPY 9 is removed as compared to the SSTLs.  The following formula will be used to calculate the percent total mass reduction: total mass above SSTLs from initial sampling less total mass above SSTLs from subsequent sampling divided by total mass above SSTLs from initial sampling.  Payment of 10 percent (10%) of the total bid price will be made upon verification (see Specifications item 10 for the method of verification) of at least one-quarter of the total CoC mass above SSTLs is removed.

The following is an example to demonstrate the CoC Mass Reduction Calculation:

| Well |  | Benzene | Toluene | Ethylbenzene | Xylene | MTBE | Naphthalene | Mass>SSTL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MW-1 | Initial A | 7,500 | 4,000 | 2,000 | 15,000 | 3,000 | 1,000 | A |
|  | SSTL B | 10 | 2,000 | 1,400 | 10,000 | 80 | 50 | B |
|  | Initial > SSTL C | 7,490 | 2,000 | 600 | 5,000 | 2,920 | 950 | 18,960 C |
|  | Subsequent D | 3,000 | 1,000 | 900 | 13,000 | 2,000 | 5 | D |
|  | SSTL E | 10 | 2,000 | 1,400 | 10,000 | 80 | 50 | E |
|  | Subsequent > SSTL F | 2,990 | 0 | 0 | 3,000 | 1,920 | 0 | 7,910 F |
| MW-4 | Initial G | 150 | 400 | 50 | 250 | 300 | 25 | G |
|  | SSTL H | 5 | 400 | 50 | 250 | 40 | 25 | H |
|  | Initial > SSTL I | 145 | 0 | 0 | 0 | 260 | 0 | 405 I |
|  | Subsequent J | 100 | 100 | 1 | 1 | 100 | 1 | J |
|  | SSTL K | 5 | 400 | 50 | 250 | 40 | 25 | K |
|  | Subsequent > SSTL L | 95 | 0 | 0 | 0 | 60 | 0 | 155 L |
| Totals | Initial > SSTL M | (sum of initial mass above SSTL for all wells) (C+I) |  |  |  |  |  | 19,365 M |
|  | Subsequent > SSTL N | (sum of subsequent mass above SSTL for all wells) (F+L) |  |  |  |  |  | 8,065 N |

# Notes: If subsequent sampling indicates a CoC concentration at or below the SSTL and/or a CoC concentration at BDL but the reporting limit is at/or below the SSTL value for any constituent, the value for the mass reduction will be 0 (no negative numbers).

If subsequent sampling indicates a CoC concentration at BDL but the reporting limit is above the SSTL, the value for any constituent will be the analytical reporting limit.

## Mass Reduction Calculation

CoC Mass Reduction =    (M-N)  =  (19,365-8,065)    = 0.5835 *100  = 58.35% CoC Reduction

(M)              19,365

(2)	50 percent total mass reduction will be achieved when one-half of the initial BTEX, MTBE, and Naphthalene mass from monitoring wells COPY 9 is removed as compared to the SSTLs.  The formula outlined in item 11. B. (1) will be used.  Payment of 10 percent (10%) of the total corrective action price will be made upon verification (see Specifications item 10 for the method of verification) of at least one-half of the total CoC mass above SSTLs is removed.

(3)	75 percent total mass reduction will be achieved when three-quarters of the initial BTEX, MTBE, and Naphthalene mass from monitoring wells COPY 9 is removed as compared to the SSTLs.  The formula outlined in item 11 B (1) will be used.  Payment of 15 percent (15%) of the total corrective action price will be made upon verification (see Specifications item 10 for the method of verification) of at least three-quarters of the total CoC mass above SSTLs is removed.

C.   	The final 25 percent (25%) of the total corrective action price will be paid upon: 1) verification that the thickness of free product does not exceed .01 foot and the levels of CoC do not exceed the site-specific target levels (SSTLs) defined in item 11.C. at any point in the area of concern (see figure #2).  Verification that the SSTLs have been met will be based upon ground-water quality samples collected from all existing monitoring wells, and additional verification wells to be installed at locations designated by DHEC (see specification #10 for more detail); and 2) all remediation and assessment items installed by the contractor (e.g., wells [including preexisting wells], trenches, etc.) are removed from the site or properly abandoned.  The SSTLs are as follows:

Site-specific target levels (SSTLs) in parts per billion (g/l)

| Well | Benzene | Toluene | Ethylbenzene | Xylenes | MTBE | Naphthalene |
| --- | --- | --- | --- | --- | --- | --- |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| MW- |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

*	Laboratory analysis is less than calculated SSTLs; therefore, SSTL mass is set equal to laboratory mass.

**	Laboratory analysis is below detection limits; therefore, SSTL mass is set equal to detection limits.

- NOTIFICATION FOR FAILURE TO PERFORM: If the contractor fails to meet any specification of corrective action as outlined in this document, DHEC will notify the contractor by certified letter of the deficiency (ies).  If the contractor does not correct the deficiency(ies) within 30 days, the contractor will be in breach of contract and the corrective action award may be voided by DHEC.  DHEC will notify the contractor by certified letter that the bid award is void and any invoices are payable upon review and approval of DHEC.  If the contractor corrects the deficiency(ies) within 30 days, the corrective action award will continue.  Please note contractor-owned items used on-site for the contract that are destroyed by acts of nature, improper maintenance or handling, theft or vandalism will not be replaced or reimbursed by the SUPERB Account.  The accepted corrective action cost bid will be final and will not be increased or cancelled for any reason (e.g., unanticipated iron fouling of a system, wells clogging because of biological activity or sediments, increased subcontractor costs, loss of utilities, modification to the system to meet the remediation goals, etc.) with the exception of unforeseen geologic circumstances or identification of additional CoC from another release. Payment will only be made for achieving the corrective action goals as specified in this contract. No interim or partial payments will be made once corrective action is initiated, except as outlined in Specification #2.

- SITE SPECIFIC DETAILS:  A brief technical summary of the release, including a location map and specifics of existing wells, is attached.  The detailed technical file will be available for review through the Freedom of Information (FOI) Office located on the third floor of the Sims Building, 2600 Bull Street, Columbia, SC. Review of the detailed technical file is not mandatory; however, offerors are strongly encouraged to review the file to ensure a complete understanding of the contract requirements. The successful bidder will be responsible for all information included in the technical file. Appointments to view the technical file may be scheduled on weekdays between the hours of 8:30 A.M. to 5:00 P.M. by calling the SCDHEC Freedom of Information Office at (803) 898-3882.  Please request file #______. NOTE: Free phase product may be present at this site. No free phase product was detected in the baseline-sampling event; however, application of corrective action technologies can result in the mobilization and possible appearance of free phase product or elevated CoC concentrations in the monitoring wells. The following facilities adjacent to the site have regulated USTs (operating/abandoned) registered with DHEC: _______________, Permit ID#, (#O/#A), _______________, Permit ID#, (#O/#A), _______________, Permit ID#, (#O/#A).

- The contractor will submit a Corrective Action Plan (CAP) within 30 days of from the date the Purchase Order is issued from the Bureau of Business Management in accordance with Specification item 2.  The implementation of the CAP will be initiated immediately upon Departmental approval of the CAP and all associated permit(s), and in accordance with the schedule presented in the CAP.  A performance bond or irrevocable standby letter of credit, equal to the award price, will be required by DHEC. The issuing institution for an irrevocable standby letter of credit must be an entity that has the authority to issue letters of credit in South Carolina and whose letter-of-credit operations are regulated and examined by a federal or state agency. The original performance bond or irrevocable standby letter of credit will be submitted to the Bureau of Land and Waste Management, UST Program, Attn: Pat Holland, within 30 days of award.  The performance bond or irrevocable standby letter of credit will specify that the SUPERB Account will be the recipient of any forfeiture. Since DHEC is responsible for the disbursement of funds from the SUPERB Account, the financial responsibility mechanism (i.e., bond or letter of credit) will be held by the Bureau of Land and Waste Management, UST Program until the work is successfully completed.

- MINIMUM REQUIREMENTS: Corrective action will be considered complete once the levels of CoC in the area of concern (see figure #2) are verified to be at or below the SSTLs listed in item 11.C., and removal or abandonment of all remediation and assessment items installed by the contractor (e.g., wells [including preexisting wells], trenches, etc.).  See Specification #10 for the method of verification.  All rehabilitation activities associated with a UST release must be performed by a SCDHEC certified Class I site rehabilitation contractor as required by R. 61-98. All corrective action plans and reports must be sealed by a Professional Engineer or Professional Geologist registered in the State of South Carolina.  All engineering reports, drawings and plans must be sealed by a Professional Engineer registered in the State of South Carolina.  All laboratory analysis for CoC must be performed by a SC certified laboratory.  All monitoring, verification, injection, or recovery wells must be installed and abandoned by a SC certified well driller.  All applicable certification, training, permits, applications, and fees associated with well installation; injection, discharge, treatment, or transportation of ground water, air, or soil; construction or operation of a remediation system; and any other action requiring a permit are the responsibility of the contractor.  Any required business or occupation license and occupational safety and health training (e.g., OSHA) as defined by the laws and regulations of the United States of America, State of South Carolina, county or city is also the responsibility of the contractor.  The terms and conditions of all applicable permits will be met.  Any contaminated ground water, soil, or construction material must be properly transported and disposed of, or treated at an approved facility with prior approval from DHEC.  Any costs for utilities construction and service (electric, telephone, sewer, etc.) required by the corrective action are the responsibility of the contractor.

SPECIFICATIONS for CORRECTIVE ACTION

All offerors must meet the following specifications as required by the proposed treatment method(s) or corrective action technology(ies):

- Submit the Corrective Action Solicitation Response.  The response will outline in general terms an approach to achieve the remediation goals (e.g., reduction of each CoC to SSTL).  The response must outline the following:

A.	A description of the proposed treatment method(s) or technology(ies) for corrective action.

B.	The estimated amount of time in months to complete site rehabilitation to meet the remediation goals, install verification wells, and remove or abandon all assessment and remediation items installed as part of corrective action.

C.	The total cost (in U. S. dollars) to complete site rehabilitation to meet the remediation goals and to remove or abandon all assessment and remediation items installed as part of corrective action.

- The successful contractor must complete and submit a detailed CAP (three copies) for the release at __________, _______________________, __________, South Carolina within 30 days from the date the Purchase Order is issued by the Bureau of Business Management.  NOTE: Use of monitoring well(s) for injection or free phase product recovery purposes is not allowed.  A condition of the plan may include installation of additional recovery, sparge, compliance, or injection wells.  The plan must define all active (pump and treat, sparge, vapor extraction, excavation of impacted soils, bioremediation, etc.) and passive (intrinsic remediation, monitoring, etc.) corrective action method(s) proposed to reduce CoC to SSTLs.  It must be shown, by use of scientific models, computations, or discussion, how each CoC will be reduced to the SSTL for each remediation method proposed for the release.  Any assumptions used in a model will be listed or shown, as well as, appropriate references. Intrinsic corrective action will require monitoring to verify remediation.  General construction details will be included (e.g., install four additional recovery wells, construct a compliance point, install four air injection wells, excavate 3,000 cubic yards of impacted soils, etc.) as well as details of well abandonment and equipment removal.  A remediation timetable including abandonment of wells and removal of equipment will be included with the CAP.  The Bureau of Land and Waste Management, UST Program will review the CAP and initiate a public notice period for a maximum of 30 days. The contractor must obtain a copy of the applicable portion of the tax map.  This map will depict the location of the facility, and all impacted properties, and all properties located adjacent to the impacted properties.  The names and addresses of the owners of each of these properties will be provided. The contractor may be required to attend or provide input at a public meeting upon request by DHEC.  Any CAP amendments and modifications arising from public notice must be submitted within 15 days of notification by DHEC.  The CAP and any amendments or modifications must be sealed by a qualified Professional Engineer or Geologist registered in the State of South Carolina.  The owner/operator, _________________, and any other affected property owners will be consulted and will approve the location of the corrective action system.  If permanent, the system must be enclosed in a fenced area or small building. The initial invoice must be received at the above address within four months or funds will be uncommitted as required by the SUPERB Act. If funds are uncommitted this invoice will be held until funding is available.

An initial monitoring report documenting CoC concentrations in all wells and potentiometric conditions prior to start up must be submitted to the Bureau of Land and Waste Management, UST Program within 45 days after award.

Based on naturally occurring conditions, the dissolved concentration of petroleum chemicals of concern (CoC) will increase or decrease.  For the purposes of this contract, the total CoC mass for the wells included in the bid package may reasonably increase up to 150 percent or decrease as much as 50 percent. If the total CoC concentration in all wells listed in Special Condition 11.B. increases more than 150 percent based on this initial sampling or if measurable free product that has not been previously documented in any report is detected during the initial sampling event, the contractor may request in writing that the award be canceled. If either of these conditions occurs, the contractor will contact the UST project manager within two days of problem identification and will submit written documentation within five days of notification. The contractor will be reimbursed for one personnel mobilization to collect samples, one sample collection and one analytical fee each monitoring well sampled as outlined in SUPERB Allowable Costs, plus $6,000 for all other costs incurred (e.g., CAP preparation, obtaining performance bond, business license). The contract will be canceled and the performance bond or irrevocable letter of credit will be returned to the company. If the total CoC concentration in all wells listed in Special Condition 11.B. decreases more than 50 percent based on this initial sampling the DHEC may cancel the award. If the corrective action system is started or treatment is performed, the contractor will be required to complete the contract unless geological conditions change or another release is confirmed. See special condition 12. If the contract is canceled by DHEC, the contractor will be notified by certified letter and an invoice for the above outlined items shall be submitted within 20 days from the date of the certified letter canceling the contract.

- Complete and submit all applications for permits (injection, NPDES, BAQC modeling form, thermal treatment, construction, etc.; 3 copies) and an engineering report (ER; 4 copies) with the CAP.  Any required permit changes or corrections will be submitted within 15 days of notification by DHEC.  The ER and any ER amendments and modifications, must be sealed by a Professional Engineer registered in the State of South Carolina.  After review of the CAP and all permit applications by DHEC, the Bureau of Land and Waste Management, UST Program will issue a notice to proceed with CAP implementation.

Implementation of the corrective action plan before the completion of the public notice process and approval of all permits by DHEC is not authorized.  If premature implementation occurs, the Department will not reimburse those costs from the SUPERB Account, and the bid award will be reduced by that amount. If the Department agrees with early implementation to better protect human health in an emergency and provides approval in writing, early implementation without any reduction to the bid amount will be authorized.

- Implement the CAP within 30 days of receipt of notice to proceed and any required permit to construct.  Disruption to the owner/operator’s normal business will be kept to a minimum.  The contractor will repair the site to the condition as it existed prior to installation of the corrective action system (e.g., asphalt paved areas will be repaved with asphalt, concrete areas will be replaced with concrete, grass areas will have soil replaced to the original grade and reseeded or sodded with grass, etc.) Upon completion of any required construction, DHEC will inspect the system and issue a permit to operate. The contractor will, at all times, keep the site free from waste materials and rubbish related to the corrective action. Until completion of the corrective action, the contractor will keep the premises in a clean, neat and workmanlike condition satisfactory to DHEC. All generated soil and wastewater will be removed from the site promptly. Manifests documenting the proper disposal of the soil and wastewater must be included in the appropriate report.

- Gain access to the adjacent property to sample monitoring wells and to install any corrective action equipment, as required. The contractor will repair the site to the condition as it existed prior to installation of the corrective action system (e.g., asphalt paved areas will be repaved with asphalt, concrete areas will be replaced with concrete, grass areas will have soil replaced to the original grade and reseeded or sodded with grass, etc.)

- Initiate system startup within 15 days of receipt of the permit to operate.  Remediation as defined in the CAP and ER will begin upon system startup.  If any problem with CAP implementation occurs, the contractor will contact the UST project manager within 24 hours of problem identification and will submit written documentation within five days of notification.  NOTE: Free phase product may be present at this site. No free phase product was detected in the baseline-sampling event; however, application of corrective action technologies can result in the mobilization and possible appearance of free phase product or elevated CoC concentrations in the monitoring wells. The following facilities adjacent to the site have regulated USTs (operating/abandoned) registered with DHEC: _______________, Permit ID#, (#O/#A); _______________, Permit ID#, (#O/#A); _______________, Permit ID#, (#O/#A).

- Complete and submit a corrective action monitoring report (3 copies plus one copy for any DHEC Bureau that issued a permit) on a quarterly basis. The first quarter corrective action monitoring report is due within 90 days of the permit to operate. The corrective action monitoring reports must include:

A.	A narrative portion that documents current site conditions, verification of system operation or CAP implementation, and system effectiveness in achieving the remediation goals (e.g., free product removal, reducing CoC to the SSTLs) as outlined in the CAP.  Any system down time and the associated reason(s) will be included in the report.

B.	Conclusions and recommendations based on the reported data.

C.	Ground-water laboratory analytical data for all monitoring wells in the following format (additional parameters such as dissolved oxygen may be required; do not sample wells containing free product):

Analytical Data (g/l)

| Monitoring Well | Date | Benzene | Toluene | Ethylbenzene | Xylenes | MTBE | Naphthalene |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MW-1 | 7/15/97 10/15/97 | 145 140 | 200 190 | 146 140 | 1,000 900 | 170 50 | 47 165 |
| MW-2 | 7/15/97 10/15/97 | 580 480 | 800 690 | 300 257 | 1,000 912 | 60 50 | 20 19 |

D.	Ground-water potentiometric data for all monitoring wells in the following format:

Ground water Data (feet)

| Monitoring Well | Date | TOC Elevation | TOC to GW | TOC to FP | FP Thickness | GW Elevation |
| --- | --- | --- | --- | --- | --- | --- |
| MW-1 | 7/15/97 10/15/97 | 98.0 98.0 | 17.54 17.90 |  |  | 80.46 80.10 |
| MW-2 | 7/15/97 10/15/97 | 100.0 100.0 | 20.50 21.50 | 20.47 21.48 | 0.03 0.02 | 79.50 78.50 |

E.	A ground-water elevation contour map of the site based on current ground-water potentiometric data.

F.	A CoC map based upon current ground-water laboratory analytical data.  The ground-water data should be adjacent to the relevant monitoring well using the following format (additional parameters such as dissolved oxygen may be required):

MW - Number

Benzene (g/l)

Toluene (g/l)

Ethylbenzene (g/l)

Xylenes (g/l)

MTBE (g/l)

Naphthalene (g/l)

G.	A copy of the DHEC approval letter and manifests for any contaminated soil and ground water removed from the site for treatment and/or disposal.

.	H.	Additional data required by permits (e.g., air analyses, wastewater effluent analyses and amounts, etc.).  The data should be reported on a form or in a format specified in the permits, and attached to the monitoring report as an addendum.

All rehabilitation activities associated with the UST release must be performed by a SCDHEC Certified Site Rehabilitation Contractor.  All air, soil, and ground-water analyses must be performed by a South Carolina certified laboratory.  The corrective action monitoring report must be sealed by a Professional Engineer or Geologist registered in the State of South Carolina.  All monitoring wells associated with the release will be sampled on a quarterly basis for the first year.  Thereafter, the number of wells sampled may be reduced and/or the interval between corrective action monitoring reports may be lengthened upon clear demonstration of CoC reduction, unless restricted by permit requirements.  Any approval to reduce the number of wells sampled or the frequency of sampling must be in writing from the UST Program.  DHEC may require data to be reported on a form or in a specific format.  The contractor will be provided with the proper report forms and format prior to system startup.  The contractor will be notified of any revisions to the report forms or format 90 days prior to the due date for the corrective action monitoring report.

- Collect one (1) ground-water sample per monitoring event for all monitoring wells associated with the release.  Each well should be purged prior to sampling.  Purging is considered complete once the ground-water temperature and pH have stabilized. Sampling logs should note all temperature and pH measurements, as well as the location and type of each sample submitted for laboratory analysis. Each ground-water sample will be collected in accordance with established QA/QC protocol and submitted to a certified laboratory for analysis.  The samples must be analyzed for the following parameters:

| Analyte | Analytical Method | Reporting Limit (g/l) |
| --- | --- | --- |
| BTEX** | 8260B/5030B | 5 |
| Naphthalene** | 8260B/5030B | 5 |
| MTBE** | 8260B/5030B | 5 |
| PAH* | 8270C/3510C | 10 |

* or EPA equivalent method that can achieve the same reporting level

** The Bureau of Land and Waste Management, UST Program no longer accepts equivalent methods for VOC analysis.

Additional samples (air, groundwater, effluent, soil) required by permits must be collected in accordance with established QA/QC protocol and submitted to a certified laboratory for analysis.  The samples will be analyzed for parameters stipulated in the permits.  Sampling and analytical data for each sample (e.g., field sampling logs, chain of custody forms, certificates of analysis, and the lab certification number) will be included in the corrective action monitoring report.

- Properly dispose of all contaminated soil and ground water generated during the implementation of the CAP and installation of verification wells.  DHEC must approve the disposal facility selected for treatment and disposal of the free product and contaminated soil and ground water. The owner/operator of the facility is considered the generator for any contaminated soil and ground water.  The contractor must document all disposal of free product and contaminated soil and ground water in the quarterly corrective action monitoring report.

- Verification for the removal of free product will be conducted by SCDHEC personnel with an interface probe.  If the remediation technology is in-situ (e.g., pump and treat, air sparging, vapor extraction): suspend operation of the system once the remediation goals for all CoC have been maintained for a period of 30 days.  Samples are to be taken after one (1) quarter or after all CoC levels have reached equilibrium and again after a second quarter. Along with the parameters listed in Specification #8, the ground-water samples should also be sampled for the following parameters:

| Analyte | Analytical Method* | Reporting Limit (g/l) |
| --- | --- | --- |
| Dissolved Oxygen | SM4500-O G | 500 |
| Ferrous Iron | SM3500-Fe D | 30 |
| Methane | Kerr Method | 1000 |
| Nitrate | 9056/9210 | 100 |
| Sulfate | 9038/9056 | 1000 |

*or EPA equivalent method that can achieve the same reporting level

- If sample results indicate that the remediation goals are not sustained, the contractor must submit a corrective action status report (3 copies) that outlines the deficiency(ies) and offers recommendations for achieving the remediation goals with a revised timetable.  Modifying and restarting of the system may be directed by DHEC. All remediation goals must be again maintained for a minimum of 30 days.  Corrective action will then be suspended again and samples taken to verify that remediation goals are sustained. This cycle of activity, including status reports, will be repeated until all CoC levels remain below SSTLs for all wells listed in Special Conditions item 11 C for two (2) consecutive quarters. (#_______) Verification wells may be installed at locations designated by DHEC.  Costs for verification well installation are considered part of this bid price.  Each well will be sampled in accordance with Specifications item 8. and the analyses compared to the calculated SSTLs for the CoC at that well location.   If the laboratory analyses are at or below the SSTLs, corrective action will be considered complete.  If any analysis is above the SSTL, the corrective action will not be considered complete, and the activity cycle described above must be repeated until all CoC levels remain below SSTLs for those wells listed in Special Conditions item 11 C. Split or duplicate samples may be collected by DHEC (or its subcontractors) to verify achievement of remediation goals. In addition to the ground water collected from the monitoring wells, the UST Program may provide up to three standards or prepared blanks for the contractor’s laboratory to analyze. The laboratory analysis from the contractor’s and the UST Program’s laboratory will be compared. In the event of substantial variance (more than 15%), a second sampling event with field and trip blanks will be sent to a SC certified laboratory by the UST Program for analysis. The contractor will be notified when the wells will be resampled, can observe this second sampling event, and will be provided analytical results for comment. DHEC Laboratory Certification will be provided copies of all sample data sets with all relevant quality assurance/quality control data to assist the UST program in determining the cause of a laboratory variation.  The Director of the Assessment and Corrective Action Division will make the final decision on which analytical values will be the basis for payment or closure based on the recommendation of the site rehabilitation contractor, DHEC Laboratory Certification, the UST Section Manager, and the UST Project Manager. The site rehabilitation contractor will be provided a written record of any decision. At least two weeks notice will be provided to the UST Project Manager prior to mobilizing to the site for sampling to verify attainment of remediation goals.   Costs for transportation and analysis of split or duplicate samples will be paid by DHEC.

or

If the remediation technology is a single event (e. g. excavation of impacted soils, vacuum enhanced recovery): collect sufficient samples as outlined in the CAP to verify the reduction of CoC to the remediation goals. The contractor may be required to install and sample (#_______) verification wells at locations designated by DHEC.   If the levels of CoC in all samples are at or below SSTLs, corrective action will be considered complete.  If the level of any CoC is above the SSTL, additional corrective action will be required.  The contractor will submit one (1) corrective action status report to document the reduction of CoC to the remediation goals.  Split or duplicate samples will be collected by DHEC (or its subcontractors) to verify achievement of remediation goals.   At least two weeks notice will be provided to the UST Project Manager prior to mobilizing to the site for sampling to verify attainment of remediation goals.   Costs for transportation and analysis of split or duplicate samples will be paid by DHEC.

- Disassemble and remove the remediation system and all associated remediation items including utilities from the site within 60 days of notification by DHEC that the remediation goal for the release associated with the UST(s) at the site has been achieved.  Disruption to the owner/operator’s normal business will be kept to a minimum.

- Properly abandon all monitoring, recovery, and/or injection wells (including preexisting wells), borings, trenches, and piping/utility runs installed by the contractor as part of corrective action within 60 days of notification by DHEC that the remediation goal for the release associated with the UST(s) at the site has been achieved.  The abandonment will be in accordance with South Carolina Well Standards and Regulations R. 61-71 and accepted industry standards for abandonment of trenches and piping/utility runs. Disruption to the property owner’s normal business will be kept to a minimum.  The contractor must notify DHEC of the method of well abandonment and final disposal of any free product and contaminated soil or ground water. The contractor will return the site to the condition prior to corrective action (e.g., asphalt paved areas will be repaved with asphalt, concrete areas will be replaced with concrete, grass areas will have soil replaced to the original grade and reseeded or sodded with grass, etc.).

CORRECTIVE ACTION SOLICITATION RESPONSE

for ___________, (UST Permit # ________), _________________, _________, South Carolina

Please respond to the following questions:

1.	The corrective action method(s) or technology (ies) that will be proposed in the CAP will be (list all active and/or intrinsic methods or technologies for remediation of the aquifer:

2.	The estimated time in months to complete the corrective action from the date of bid award, corrective action goals are met, and all corrective action items are removed from the site or properly abandoned is approximately                         months. This time assumes all submitted plans and reports will be reviewed by DHEC within 30 days of receipt.

3.	The total cost in dollars, regardless of the type, quantity, or duration of the permitted technology applied, to treat the area of concern (see figure #2) such that the thickness of free product does not exceed .01 foot and the levels of CoC do not exceed the site-specific target levels (SSTLs) defined in item 11.C. at any point, complete all associated monitoring and post-remediation verification, prepare all plans, reports, and correspondence; obtain and meet all terms and conditions of all required permits and licenses; design, install, monitor, operate, maintain, and when completed, properly abandon or remove all assessment and remediation items installed as part of corrective action; provide evidence of performance bond; and other items outlined in this solicitation is:  $

ACCEPTANCE and DELIVERY STATEMENT

In compliance with the solicitation and subject to all conditions thereof, the offeror agrees, if this bid is accepted within                        days from date of opening, to complete the corrective action as specified at the price set forth.

For the purpose of this submittal and acceptance of financial approval should it occur, I certify that this company understands the nature of the release and the geologic conditions at this facility as documented in the technical file and this solicitation. Additionally, I certify that this company understands that acceptance is based on total cost to treat the area of concern.

_______________________________________________		Certification No. ______________________

Contractor (Print)

_______________________________________________		____________________________________

Authorized Representative (Print)					Signature